## Sheet1
Table 3. Task and assignment breakdown by week and by project milestone.
| Group: | Doggy Adoption Network (DAN)
| Team Members (and initials): | Elizabeth Bailey (EB), Evan Parisier (EP), Jack White (JW), Nathan Malamud (NM)
| Date this was last updated: | June 6th
| Last updated by (whom): | NM
| Milestone | Assigned to (whom) | Time Spent (hours) | Date Due | Date Completed | Date Assigned | Notes | Status
Week 1
| Exchange phone numbers. Schedule first in-person meeting over text. | All | 0.5 | May 5th | May 5th | May 5th |  | completed
Week 2
| Initial SRS Draft | NM, EB | 2 | May 9th | May 9th | May 5th |  | completed
| Initial SDS Draft | NM, EP | 2 | May 9th | May 9th | May 5th | Specific changes listed on SDS revision history | completed
| Initial Project Plan | NM, JW, EB | 2 | May 9th | May 9th | May 5th
| Interview Local Animal Shelters | NM | 5 |  |  | May 9th |  | completed
| Interview a veterinarian | EB | 1 |  |  | May 9th |  | completed
Week 3
| Interview Volunteers at GreenHill "Bark in the Park" Fundraiser | EB, JW | 3 | May 15th | May 15th | May 10th |  | completed
| SRS/SDS/Project Plan Draft 2 | All | 4 | May 16th | May 16th | May 5th |  | completed
Week 4
| In-person Brainstorming Meeting | All | 2 |  | May 27th |  | Designed quiz questions based on prior research | completed
Week 5
| Generate dog profiles | NM | 3 |  |  | May 27th |  | completed
| Design Filter Module | NM | 3 |  |  | May 27th |  | completed
| Set up SQL Database | EP | 2 |  |  | May 9th |  | completed
| Set up basic window views | EB | 10 |  | May 30th | May 9th |  | completed
| Design Quiz Module | JW | 5 |  |  |  |  | completed
| Create Data Handling System (middleware) for quiz and dog info | All
| Link DB, Data Handling w/ front end | All | 10 |  |  |  | Decided to use regular python mysql connector rather than Flask one | completed
| Create login page and functionality, link to quiz | JW
| Test system and make appropriate bug fixes | All
Week 6
| Fix bug in dog profile display route | EB | 4 | ASAP
| Final Project Submission |  | 2 | June 6th |  |  |  | completed
| Project Presentation (Optional) |  | 0 | June 6th |  |  |  | completed